## CONSTRUCTION CHANGE
Construction Change Log
Project Name: |  |  |  |  | Date Updated: |  | MM/DD/YYYY
Contract #: |  |  |  |  | Updated By:
Contractor: | [5 empty] | Today's Date: | 2026-10-26
GLWA Project Manager: |  |  |  |  | PCML:
Change Type/# | Description of Change | Proposed Schedule Impact (days) | Proposed Cost Impact ($) | Negotiated Schedule Impact (days) | Negotiated Cost Impact ($) | Category | Date Initiated | Date Completed | Change Status | Days Open | CO No. | CO Approval Date (MM/DD/YYYY)
CR 01 |  | 40 | 10000 | 25 | 10000 |  | 2018-03-12 | 2018-04-15 | Closed | 34 | N/A | N/A
CD 01 |  | 0 | 25000 | 0 | 18000 |  | 2018-03-20 | 2018-04-15 | Approved | 26 | 1 | 2018-05-10
FO 01 |  | 10 | 12500 | 10 | 15000 |  | 2018-03-25 | 2018-05-28 | Approved | 64 | 2 | TBD
CR 02 |  | 45 | 0 | 37 | 0 |  | 2018-04-02 | 2018-04-15 | Approved | 13 | 1 | 2018-05-10
CD 02 |  | 20 | 8500 |  |  |  | 2018-06-05 | 2018-07-15 | Closed | 40 | 3 | TBD
FO 02 |  | 10 | 0 | 15 | 0 |  | 2018-07-01 | 2018-07-15 | Approved | 14 | 3 | TBD
|  | 125 | 56000 | 87 | 43000
NOTES:
CHANGE TYPE: CR (Change Request), CD (Change Directive), FO (Field Order)
CHANGE STATUS: Potential, Proposed, Approved, Closed
CHANGE CATEGORY: OR (Owner Request), DSC (Differing Site Conditions), DE (Design Error), DO (Design Omission), RR (Regulatory Requirements), Other
Auto Calculating Cell or Cell with Dropdown Menu

## PROFESSIONAL SERVICES
Professional Services Contract Change Log
Project Name: | [8 empty] | Date Updated: |  | MM/DD/YYYY
Contract #: | [8 empty] | Updated By:
Consultant: | [8 empty] | Today's Date:
GLWA Project Manager: | [8 empty] | PCML:
Change Type/# | Description | Date Initiated | Project Phase |  |  |  | Task | Task Name | Subtask | Subtask Name | Estimated Impact |  | Negotiated Impact |  | Date Completed | Days Open | Status | CO Number | CO Approval Date | Comments
|  |  | Planning | Design | Proc. | Constr. |  |  |  |  | Time | $ | Time | $ |  |  |  | Number | Number
Task Change Impact
CD 01
Task Change Impact
CR 02
Task Change Impact
Contract Change Impact | [10 empty] | 0 | 0 | 0 | 0
NOTES:
CHANGE TYPE: CR (Change Request), CD (Change Directive), FO (Field Order)
CHANGE STATUS: Potential, Proposed, Approved, Closed
Auto Calculating Cell or Cell with Dropdown Menu

## DROPDOWNS
CHANGE STATUS | CHANGE CATEGORY
Potential | OR
Proposed | DSC
Approved | DE
Closed | DO
RR
Other