## Instructions
Trinity River Authority
Vendor Instructions
Offeror shall complete each tab in this workbook and submit the completed workbook with its proposal response. Responses should be concise, specific, and directly aligned to the Scope of Work for RFP XXXXXXXX. The implementation plan should describe how the Offeror will deliver the Infor FSM Migration and new products GHR, WFM and Payroll, including project governance, requirements validation, configuration, integrations, data migration approach, testing, training, organizational change management, go-live, post go live support, resource needs, risks, and deliverables. Offerors shall not modify the tab names, column headings, or required response structure. Supplemental materials may be provided separately; however, the primary implementation response must be completed in this workbook. The tab "Modules/Processes is for reference to scope of the effort.

## Modules-Processes
Level 1 (Process Area) | Level 2 (Process - Flowchart) | Level 3 (Workflow Activities) | Module
Expense Management
| Expense Reports, OCR Premium for Expense Reporting, Travel Plans, Hotel Folio |  | Expense Management
Velocity Suite Tier 1
| Velocity Suite Tier 1 |  | Velocity Suite Tier 1
EUNA
| Core, Openbook, Digital Budgetbook) |  | Euna
Record to Report
Journal Entry to Post
|  | Record or Maintain Journal Entry | Global Ledger
|  | Approve or Reject Journal Entry | Global Ledger
|  | Release Journal Entry | Global Ledger
|  | Post Journal Entry | Global Ledger
|  | Update Cubes | Global Ledger
|  | Account Analysis | Global Ledger
|  | Business Intelligence Financial Reports | Global Ledger
|  | Reverse Journal Entry | Global Ledger
Recurring Journal to Release
|  | Recurring Journal | Global Ledger
|  | Unrelease and Update | Global Ledger
|  | Recurring Journal Release | Global Ledger
|  | Journalize Recurring Journal | Global Ledger
|  | Approve or Reject | Global Ledger
|  | Unprocess Recurring Journal | Global Ledger
Allocation Creation to Journalize
|  | Allocation Control | Allocations
|  | Allocation Lines | Allocations
|  | Budget Allocation Control | Allocations
|  | Budget Allocation Lines | Allocations
|  | Run Allocations | Allocations
|  | Listing Report | Allocations
|  | Calculation Listing | Allocations
|  | Journalize Allocations | Allocations
External General Ledger Transaction Interface
|  | SFTP File to Server | Global Ledger
|  | Import GL Transactions via DB import | Global Ledger
|  | Transaction Interface Maintenance | Global Ledger
|  | Interface Selected Run Groups | Global Ledger
|  | Interface Run Results | Global Ledger
External Budget Import to Processing
|  | Import Budget Lines | Global Ledger
|  | Set Ready Scenario | Global Ledger
|  | Activate Budget Edit Template | Global Ledger
Subsystem Posting to Global Ledger Update
|  | Post Journal Entry | Global Ledger
|  | Update Cubes | Global Ledger
|  | Account Analysis | Global Ledger
Project Creation to Reporting
Project Creation to Maintenance
|  | Summary Project | Project Ledger
|  | Person Responsible or Responsible Team | Project Ledger
|  | Posting Project | Project Ledger
|  | Period of Performance | Project Ledger
|  | Project Personnel Posting Project | Project Ledger
Request Posting Project to Maintenance
|  | Request New Posting Project | Project Ledger
|  | Approve or Reject | Project Ledger
Project Funding Source Creation to Maintenance
|  | Summary Funding Source | Project Invoicing & Revenue
|  | Person Responsible or Responsible Team | Project Invoicing & Revenue
|  | Posting Funding Source | Project Invoicing & Revenue
|  | Funding Source Deliverables | Project Invoicing & Revenue
|  | Grant Reporting | Project Invoicing & Revenue
|  | Intercompany Billing | Project Invoicing & Revenue
Billable Project Contract to Maintenance
|  | Project Contract | Project Invoicing & Revenue
|  | Add Funding Source to Project Contract Funding Source | Project Invoicing & Revenue
|  | Funding Source Retainer | Project Invoicing & Revenue
|  | Funding Source Milestone | Project Invoicing & Revenue
|  | Funding Source Installment | Project Invoicing & Revenue
Request Project Status Change
|  | Request Project Status Change | Project Ledger
|  | Approve or Reject | Project Ledger
Billing to Collections
Customer Maintenance
|  | Customer | Grant Accounting
|  | Company Customer | Grant Accounting
|  | Customer Bill To | Grant Accounting
|  | Maintain Customer | Grant Accounting
|  | Request New Customer | Grant Accounting
|  | Request Change to Customer | Grant Accounting
|  | Approve or Reject | Grant Accounting
Billing Invoice Creation to Release
|  | Create Batch | Billing
|  | Enter Invoice | Billing
|  | Release Invoice | Billing
|  | Invoice Verification Report | Billing
|  | Invoice and Register Print | Billing
|  | Billing Subsystem Update | Billing
Billing Recurring Invoice Creation
|  | Billing Recurring Invoice Definition | Billing
|  | Billing Customer Recurring Invoice | Billing
|  | Create Recurring Invoices | Billing
External Invoice Interface to Release
|  | SFTP File to Server | Receivables
|  | Import Receivable Invoices via DB Import | Receivables
|  | Receivable Invoice Interface Maintenance | Receivables
|  | Receivable Invoice Interface | Receivables
|  | Receivable Invoice Interface Results | Receivables
Project Invoice Creation and Revenue Recognition
|  | Paid Invoice Project Update | Grant Accounting
|  | Remove Indirect Burden AP Hold | Grant Accounting
|  | Generate Contract Invoices | Grant Accounting
|  | Validate Invoice Journal Entries | Grant Accounting
|  | Delete Created Invoice | Grant Accounting
|  | Journalize Invoice | Grant Accounting
|  | Recognize Contract Revenue | Grant Accounting
|  | Validate Revenue Journal Entries | Grant Accounting
|  | Delete Revenue | Grant Accounting
|  | Journalize Contract Revenue | Grant Accounting
Receivables Payment 2 Interface
|  | SFTP File to Server | Grant Accounting
|  | Import External Payments via DB Import | Grant Accounting
|  | Receivables Payment 2 Maintenance | Grant Accounting
|  | Interface Payments | Grant Accounting
|  | Payment 2 Interface Results | Grant Accounting
Payment Processing to Maintenance
|  | Payment Batch | Grant Accounting
|  | Apply Payments to Invoices | Grant Accounting
|  | Release Batch | Grant Accounting
|  | Cash Batch Release Report | Grant Accounting
|  | Return To Maker | Grant Accounting
|  | Release Return To Maker | Grant Accounting
|  | Payment Transfer | Grant Accounting
|  | Payment Reversal | Grant Accounting
|  | Application Reversal Creation | Grant Accounting
|  | Automatic Cash Application | Grant Accounting
|  | Application Close | Grant Accounting
|  | Journalize | Grant Accounting
Receivable Invoice Creation to Release
|  | Receivable Invoice Batch | Receivables
|  | Receivable Invoice | Receivables
|  | Receivable Invoice Release | Receivables
|  | Receivable Invoice Print | Receivables
|  | Journalize Invoice | Receivables
Intercompany Billing Invoice to Settlement
|  | Intercompany Billing Document | Intercompany Billing
|  | Approve or Reject | Intercompany Billing
|  | Release Intercompany Billling Document | Intercompany Billing
|  | Intercompany Billing Payment Settlement | Intercompany Billing
|  | Automatic Cash Application | Receivables
|  | Journalize | Receivables
|  | Payment Close | Payables
Intercompany Billing Transfer Pricing to Calculate
|  | Intercompany Billing Transfer Recharge | Intercompany Billing
|  | Intercompany Billing Recharge Types | Intercompany Billing
|  | Intercompany Billing Global Bill To Entities | Intercompany Billing
|  | Intercompany Billing Transfer Weights | Intercompany Billing
|  | Intercompany Billing Calculate Recharges | Intercompany Billing
|  | Intercompany Billing Interface Recharges | Intercompany Billing
Credit to Collections
|  | Customer Review Selection | Grant Accounting
|  | Credit Analyst Customer Review | Grant Accounting
|  | Adjustments Exceeded Review | Grant Accounting
|  | Adjustment Maintenance | Grant Accounting
|  | Customer Aging Report | Grant Accounting
Asset Creation to Maintenance
Asset Creation to Release
|  | Create Asset From Template | Project Ledger
|  | Project Interface Control | Project Ledger
|  | Draft Project Interface | Project Ledger
|  | Edit and Summarize Transations | Project Ledger
|  | Project Capitalization Interface | Project Ledger
|  | Create Asset From Payables | Project Ledger
|  | Asset Interface | Project Ledger
|  | Release Asset | Project Ledger
|  | Submit for Approval | Project Ledger
|  | Approve or Reject | Project Ledger
Maintain Asset
|  | Adjust an Asset | Asset Accounting
|  | Transfer an Asset | Asset Accounting
|  | Dispose an Asset | Asset Accounting
|  | Reinstate an Asset | Asset Accounting
|  | Release Asset | Asset Accounting
|  | Submit for Approval | Asset Accounting
|  | Approve or Reject | Asset Accounting
|  | Asset Disposal Report | Asset Accounting
External Asset Import to Release
|  | SFTP File to Server | Asset Accounting
|  | Import External Assets via DB | Asset Accounting
|  | Asset Import Group List | Asset Accounting
|  | Perform Asset Interface | Asset Accounting
|  | Asset Management Interface Results | Asset Accounting
|  | Asset Item Adjustment Import | Asset Accounting
|  | Additional Item Interface | Asset Accounting
|  | Release Asset | Asset Accounting
Cash Processing to Reconciliation
Cash Forecasting to Analysis
|  | Direct Forecast | Cash Management
|  | Cash Forecast | Cash Management
|  | Approve or Reject | Cash Management
|  | Forecast Analysis | Cash Management
Cash Management Transactions to Release
|  | Cash Ledger Transaction | Cash Management
|  | Release Cash Ledger Transaction | Cash Management
|  | Batch Approval | Cash Management
|  | Approve or Reject | Cash Management
|  | Cash Receipt | Cash Management
|  | Release Cash Ledger Receipt | Cash Management
|  | Cash Ledger Payment | Cash Management
|  | Release Cash Ledger Payment | Cash Management
|  | Journalize | Cash Management
|  | Electronic Funds Transfer Transaction Entry | Cash Management
|  | Release Electronic Funds Transfer | Cash Management
|  | EFT Extract File Creation | Cash Management
|  | Bank Fund Transfer | Cash Management
|  | Release Bank Fund Transfer | Cash Management
|  | Internal Wire Transfer | Cash Management
|  | Release Wire Transfer | Cash Management
|  | Wire Transfer Output Files | Cash Management
Interface Cash Ledger Payments and Transactions
|  | SFTP File to Server | Cash Management
|  | Import Cash Ledger Transactions to DB Import | Cash Management
|  | Interface Selected Cash Ledger Run Groups | Cash Management
|  | Cash Transaction Interface Results | Cash Management
|  | Cash Ledger Transaction Interface | Cash Management
Daily Bank Statement to Reconciliation
|  | Manual Bank Statement and Lines | Bank Statement Reconciliation
|  | Bank Statement Interface | Bank Statement Reconciliation
|  | Imported Bank Statement and Lines | Bank Statement Reconciliation
|  | Bank Statement Reconciliation | Bank Statement Reconciliation
|  | Release Bank Statement Line Distributions | Bank Statement Reconciliation
|  | Reconciliation Variance Adjustment | Bank Statement Reconciliation
|  | Close Bank Statement | Bank Statement Reconciliation
|  | Journalize | Bank Statement Reconciliation
Maintain Cash Management Transaction
|  | Void Cash Ledger Transaction | Cash Management
|  | Approve or Reject | Cash Management
|  | Cancel Cash Ledger Transaction | Cash Management
|  | Reconcile Cash Ledger Transaction | Cash Management
|  | Write Off Transaction | Cash Management
|  | Void or Stop Payment | Cash Management
|  | Payment Void Stop Pay Update | Cash Management
|  | Returned Payment Entry | Cash Management
|  | Journalize | Global Ledger
Stale Date and Escheatment Processing
|  | Stale Date Processing | Cash Management
|  | Stale Date Output Files | Cash Management
|  | Manual Stale Date | Cash Management
|  | Escheatment Processing | Cash Management
|  | Escheatment Output Files | Cash Management
|  | Generate IDM Escheatment Notice | Cash Management
|  | Manual Escheatment | Cash Management
Lease Creation to Termination
Lease Creation to Release
|  | Lease Creation | Lease Accounting
|  | Lease Payment Schedule | Lease Accounting
|  | Classify Lease | Lease Accounting
|  | Leased Asset | Lease Accounting
|  | Release Lease | Lease Accounting
|  | Lease Modification | Lease Accounting
|  | Lease Adjustment | Lease Accounting
|  | Lease Renewal | Lease Accounting
|  | Change the Lessor on a Lease | Lease Accounting
|  | Terminate a Lease | Lease Accounting
|  | Close a Lease | Lease Accounting
Lease Invoices to Lease Payments
|  | Create Payables Invoices for Lease Payments | Lease Accounting
|  | Lease Payment Approval | Lease Accounting
|  | Lease Payment Invoices to Payables | Lease Accounting
|  | Lease Interest Calculation | Lease Accounting
|  | Lease Posting | Lease Accounting
External Lease Interface
|  | Lease Payment Schedule Import | Lease Accounting
|  | Lease Interface | Lease Accounting
Sublease Create to Process
|  | Sublease Creation | Lease Accounting
|  | Sublease Invoices | Lease Accounting
|  | Sublease Period Processing | Lease Accounting
|  | Journalizing Sublease Transactions | Lease Accounting
|  | Close a Sublease | Lease Accounting
Source to Settle
Supplier Registration to Validation
|  | Supplier Registration | Supplier Portal
|  | Supplier Record Request Validation | Strategic Sourcing
|  | Supplier Approval | Strategic Sourcing
|  | Create Vendor from Supplier | Strategic Sourcing
Create Event to Award Output
|  | Create Event | Strategic Sourcing
|  | Approve or Reject | Strategic Sourcing
|  | Respond and Post Questions | Strategic Sourcing
|  | Create Amendment | Strategic Sourcing
|  | Supplier Response | Strategic Sourcing
|  | Response Analysis | Strategic Sourcing
|  | Award Event | Strategic Sourcing
|  | Assign Non Award Reason Code | Strategic Sourcing
|  | Approve or Disapprove Final Award | Strategic Sourcing
|  | Create Output | Strategic Sourcing
Contract Creation to Execution
|  | Propose New Contract | Supplier Portal
|  | Create Contract Manually | Contract Management
|  | Create Contract using Wizard | Contract Management
|  | Create Contract from Contract | Contract Management
|  | Create Contract from Template | Contract Management
|  | Create Contract from Interview | Contract Management
|  | Create Contract from an Event | Contract Management
|  | Add or Edit Contract Details | Contract Management
|  | Approve or Reject | Contract Management
|  | Negotiate Terms | Contract Management
|  | Create Contract Document | Contract Management
|  | Email Contract to Supplier | Contract Management
|  | Unrelease or Approve or Reject | Contract Management
|  | Activate Contract | Contract Management
Contract Change Order to Contract Completion
|  | Create a Change Order | Contract Management
|  | Review Change Order | Contract Management
|  | Release Addendum or Amendment | Contract Management
|  | Unrelease or Approve or Reject | Contract Management
|  | Activate Contract | Contract Management
Contract Monthly Maintenance
|  | Run Load Invoice Rebate Invoice Program | Contract Management
|  | Run Perform Rebate Calculation | Contract Management
|  | Enter Vendor Rebate Submission | Contract Management
|  | Run Load PO Invoice Line Data | Contract Management
|  | Change Tier Assignment | Contract Management
Contract Maintenance to Completion
|  | Create Contract Amendment | Contract Management
|  | Create Contract Addendum | Contract Management
|  | Unrelease or Approve or Reject | Contract Management
|  | Activate Contract | Contract Management
|  | Contract or Contract Line Hold | Contract Management
|  | Contract Close | Contract Management
Request New Vendor to Manage Vendor
|  | Request New Vendor | Payables
|  | Approve or Reject | Payables
|  | Request Update Vendor | Payables
|  | Request Update Vendor Location | Payables
Vendor Creation to Maintenance
|  | Create Vendor from Supplier | Strategic Sourcing
|  | Supplier Vendor Compare | Strategic Sourcing
|  | Manage Vendor | Payables
|  | Create Vendor | Payables
Create Purchasing Vendor
|  | Create Purchasing Vendor | Purchasing
|  | Create Purchasing Vendor Locations | Payables
Requisition to Approval
|  | Create Requisition | Requisition
|  | Unrelease or Approve or Reject | Requisition
Interface Requisitions
|  | SFTP File to Server | Purchasing
|  | Import Requisitions File to Work File | Purchasing
|  | Import Requisitions File to DB | Purchasing
|  | Interface Requistions | Purchasing
|  | Interface Requisition Results | Purchasing
|  | Requisition Interface Maintenance | Purchasing
Purchase Order to Receipt
|  | Process Purchase Request | Purchasing
|  | Manage Purchase Request | Purchasing
|  | Create Purchase Order | Purchasing
|  | Unrelease or Approve or Reject | Purchasing
|  | Issue PO to Vendor | Purchasing
|  | Receive Items | Purchasing
|  | Unreleased Receiving Buyer Message | Purchasing
|  | Release Receipt | Purchasing
|  | Two Step Receiving | Purchasing
|  | Release and Print Delivery and Putaway Tickets | Purchasing
|  | Receipt Adjustment | Purchasing
|  | Inspection | Purchasing
Interface Purchase Orders
|  | SFTP File to Server | Purchasing
|  | Import Purchase Order File to Work File | Purchasing
|  | Import Purchase Order File to DB | Purchasing
|  | Interface Purchase Orders | Purchasing
|  | Interface Purchase Order Results | Purchasing
|  | Purchase Order Interface Maintenance | Purchasing
Interface Receipts
|  | SFTP File to Server | Purchasing
|  | Import Receipts File to Work File | Purchasing
|  | Import Receipts File to DB | Purchasing
|  | Interface Receipts | Purchasing
|  | Receipts Interface Results | Purchasing
|  | Receipt Interface Maintenance | Purchasing
Procurement Card Processing
|  | Enter New Procurement Card Request | Procurement Card
|  | Approve or Reject | Procurement Card
|  | Define Card Holder Information and Activate Card | Procurement Card
Procurement Card Transaction to Payment
|  | Bank Statement File FTP to Server | Procurement Card
|  | Import Bank Statement to Workfile | Procurement Card
|  | Import Bank Statement to DB Import | Procurement Card
|  | Load Interface Procurement Card Statement | Procurement Card
|  | Procurement Card Interface Maintenance | Procurement Card
|  | Release and Invoice Procurement Card Transactions | Procurement Card
|  | Procurement Card Charges | Procurement Card
Return Item to Vendor
|  | Create Vendor Return | Purchasing
|  | Edit Vendor Return | Purchasing
|  | Authorize Vendor Return | Purchasing
|  | Ship Vendor Return | Purchasing
|  | Print Vendor RMA | Purchasing
|  | Chargeback Created | Purchasing
|  | Journalize | Purchasing
Invoice to Match
|  | Invoice with Match Template | Invoice Matching
|  | Invoice with Service Contract Template | Invoice Matching
|  | Submit for Approval | Invoice Matching
|  | Approve or Reject | Invoice Matching
|  | Rejected Invoices List | Invoice Matching
|  | PO Unit Cost Correct YES | Invoice Matching
|  | Forward | Invoice Matching
|  | PO Unit Cost Correct NO | Invoice Matching
|  | Assign to Worklist | Invoice Matching
|  | Reconcile Invoice | Invoice Matching
|  | Approve Reconciliation Message | Invoice Matching
|  | Create Chargeback | Invoice Matching
|  | Forward | Invoice Matching
|  | Match Invoice | Invoice Matching
|  | Automatch | Invoice Matching
|  | Automatch Results | Invoice Matching
|  | Review Errors | Invoice Matching
Match Invoice Interface
|  | SFTP File to Server | Invoice Matching
|  | Import Invoice to Work File | Invoice Matching
|  | Import Invoice to DB Import | Invoice Matching
|  | Match Invoice Interface | Invoice Matching
|  | Match Invoice Interface Results | Invoice Matching
|  | Match Interface Invoice Maintenance | Invoice Matching
|  | Automatch | Invoice Matching
Document Management Interface
|  | Document Management Interface Maintenance | Infor Document Management
|  | Interface Document Management Invoices | Infor Document Management
|  | Document Management Interface Maintenance Results | Infor Document Management
Invoice to Approval
|  | Create Invoice | Payables
|  | Submit for Approval | Payables
|  | Approve or Reject | Payables
|  | Rejected Invoices List | Payables
|  | Release Payables Invoice | Payables
External Payable Invoice Interface to Release
|  | SFTP File to Server | Payables
|  | Import Payables Invoice to DB Import | Payables
|  | Interface Payables Invoices | Payables
|  | Payables Invoice Interface Results | Payables
|  | Payables Interface Invoice Maintenance | Payables
Request Invoice Payment to Approval
|  | Request Invoice Payment | Payables
|  | Approve or Reject | Payables
Invoice Maintenance
|  | Update Invoice | Payables
|  | Cancel Invoice | Payables
|  | Invoice Unmatch | Invoice Matching
|  | Purchase Order Invoice Cancel | Invoice Matching
|  | Restore Rejected Invoice | Invoice Matching
|  | Amend Matched Invoice | Invoice Matching
|  | Reinstate Cancelled Invoice | Invoice Matching
|  | Release Matched Invoice | Invoice Matching
|  | Payment Void Stop Pay Update | Invoice Matching
Invoice Selection to Payment Close
|  | Perform Cash Requirements | Payables
|  | Cash Requirement Results | Payables
|  | Payment Clearing File Creation | Payables
|  | Electronic Payment Creation | Payables
|  | Cash Payment Register | Payables
|  | Payment Close | Payables
|  | Paid Invoice Project Update | Payables
|  | Start Cash Requirements | Payables
|  | Select Payments | Payables
|  | Schedule Payments | Payables
|  | Complete Payment Cycle | Payables
|  | Positive Pay File Creation | Payables
Reportable Income US 1099 Maintenance to Year End Processing
|  | View Reportable Income | Payables
|  | Maintain Reportable Income | Payables
|  | US 1099 Tape Creation | Payables
|  | View US 1099 Tape Output Files | Payables
Plan to Inventory
Inventory Count to Report
|  | Manage Select IDs | Inventory Control
|  | Mass Freeze Items | Inventory Control
|  | View and Print Count Sheets | Inventory Control
|  | Enter Counts | Inventory Control
|  | Enter Variance Reasons | Inventory Control
|  | Inventory Variance Update - Update Equals No | Inventory Control
|  | Inventory Variance Update - Update Equals Yes | Inventory Control
|  | Delete Freeze Records | Inventory Control
|  | View Accuracy | Inventory Control
|  | Inventory Count Control Status | Inventory Control
|  | Journalize | Inventory Control
Item Request to Creation
|  | Request New Item | Inventory Control
|  | Approve or Reject | Inventory Control
|  | Create New Item | Inventory Control
Item Location Request to Creation
|  | Request New Item Location | Inventory Control
|  | Approve or Reject | Inventory Control
|  | Create Item Location | Inventory Control
Inventory Transactions
|  | Create Inventory Receipt | Inventory Control
|  | Create Inventory Issue | Inventory Control
|  | Create Inventory Adjustment | Inventory Control
|  | Bin Transfer | Inventory Control
|  | Create Inventory Transfer or Inventory In-Transit Transfer | Inventory Control
|  | Create In Transit Shipping Document | Inventory Control
|  | In Transit Receiving | Inventory Control
|  | Cost Adjustment | Inventory Control
Interface Inventory Transactions
|  | Transaction Interface Maintenance | Inventory Control
|  | Interface Inventory Transactions | Inventory Control
|  | Transaction Interface Results | Inventory Control
Demand to Replenish
|  | Bin Replenishment Report | Inventory Control
|  | Location Replenishment Report | Inventory Control
|  | Replenishment by Requisition | Inventory Control
|  | Inventory Vendor Reorder Advice | Inventory Control
|  | Replenishment Purchase Order Request | Inventory Control
Reconciliation to Close
Close Management Schedule Process
|  | Schedule Process | Close Management
|  | Open Period for Work | Close Management
|  | Close Management Update and Notify | Close Management
|  | Start Task | Close Management
|  | Complete Task | Close Management
|  | Approve or Reject | Close Management
|  | Close Management Update and Notify | Close Management
Purchasing Period Close
|  | Requisition Status Report | Purchasing
|  | Release and Approve Purchasing Receiving | Purchasing
|  | Received not Invoiced Report or Update | Purchasing
|  | Matched not Received Report or Update | Invoice Matching
|  | Invoiced not Received Report | Invoice Matching
|  | Close Purchase Order Header | Purchasing
|  | Purchasing System Close | Purchasing
Billing Period Close
|  | Billing Subsystem Update | Billing
|  | Billing System Close | Billing
Receivables Period Close
|  | Application Close Receivables | Receivables
|  | Journalize | Receivables
|  | Period Close Report | Receivables
|  | Transaction Status Update | Receivables
|  | Receivables Tie Back Report | Global Ledger
|  | Finance Charge | Receivables
|  | Advanced Dunning Letter Selection | Receivables
|  | Statement Print | Receivables
Lease Accounting Period Close
|  | Lease Posting | Lease Accounting
|  | Lease Period Close | Lease Accounting
Payables Period to Year End Close
|  | Payables Recurring Invoice Update | Payables
|  | Journalize | Payables
|  | Invoice Accrual Reconciliation Report | Payables
|  | Close Period in Payables | Payables
|  | Vendor Balance Year End | Payables
Inventory Period Close
|  | Release Inventory Transactions | Inventory Control
|  | Journalize | Inventory Control
|  | Period Close | Inventory Control
|  | Close Inventory Control | Inventory Control
|  | Period End Valuation | Inventory Control
|  | Inventory Turnover by Issues | Inventory Control
|  | Potential Obsolete | Inventory Control
|  | Potential Overstock | Inventory Control
Cash Period Close
|  | Journalize | Cash Management
|  | Bank Period Close | Bank Statement Reconciliation
|  | Cash Ledger Company Period Close | Cash Management
|  | Stale Dating and Escheatment Report | Cash Management
Asset Period to Year End Close
|  | Asset Depreciation Calculation and List | Asset Accounting
|  | Asset Close Period | Asset Accounting
|  | Close Year | Asset Accounting
Projects Period Close
|  | Paid Invoice Project Update | Project Invoicing & Revenue
|  | Projects System Control | Project Ledger
Transaction to Reconciliation
|  | Bank Statement Reconciliation | Bank Statement Reconciliation
|  | Reconcile AP Accrual Accounts | Payables
|  | Reconcile Prepaid Accounts | Payables
|  | Reconcile Asset Accounts | Asset Accounting
|  | Reconcile all Other Accounts | Global Ledger
Global Ledger Period to Year End Close
|  | Recurring Journal Period Close | Global Ledger
|  | Cost Allocation Period Close | Allocations
|  | Post Journal Entry | Global Ledger
|  | Currency Translation or Revalue | Global Ledger
|  | GL Period Close | Global Ledger
|  | Close Reporting Basis | Global Ledger
Recruit to Onboard
Position to Requisition
|  | Request Position | Global Human Resources
|  | Request New or Edit Requisition | Global Human Resources
|  | Request Update to Requisition | Manager Space
|  | Update Auto Created Requisition | Manager Space
|  | Review Requisition Request (Parent Manager) | Talent Acquisition
|  | Review Requisition Request (PBM) | Talent Acquisition
|  | Update Position Budget (PBM) | Talent Acquisition
Candidate to Offer
|  | Prepare and Post Requisition | Talent Acquisition
|  | Add A Candidate | Talent Acquisition
|  | Attach A Candidate | Talent Acquisition
|  | Candidate Apply | Talent Acquisition
|  | Screen Candidate(s) | Talent Acquisition
|  | Schedule or Update Interview (Recruiter) | Talent Acquisition
|  | Manager Review Candidate(s) | Manager Space
|  | Schedule or Update Interview (Hiring Manager) | Manager Space
|  | Candidate Selects Interview Timeslot | Talent Acquisition
|  | Define or Edit Offer | Talent Acquisition
|  | Review Offer Request | Talent Acquisition
|  | Create and Extend Offer Letter | Talent Acquisition
|  | Candidate Reviews Offer | Talent Acquisition
|  | Candidate Completes Preboarding | Transition Management
|  | Validate Preboarding Tasks | Talent Acquisition
|  | Disposition Candidate(s) | Talent Acquisition
Hire to Assign
|  | Request or Edit Hire | Talent Acquisition
|  | Request or Edit Rehire | Talent Acquisition
|  | Request or Edit Transfer/Promote | Talent Acquisition
|  | Request or Edit Add Assignment | Talent Acquisition
|  | Review Hire Action Request (HR Admin) | Talent Acquisition
|  | Review Hire Action Request (PBM) | Talent Acquisition
|  | Resource Completes Onboarding | Transition Management
|  | Resource Completes Crossboarding | Transition Management
|  | Validate Resource Transition Tasks | Transition Management
|  | Undo Hire | Talent Acquisition
Employee Administration to Benefits
Jobs to Positions
|  | Request a New Job | Manager Space
|  | Review Request (Compensation Analyst) | Compensation
|  | Request a New Position | Manager Space
|  | Review Request (Parent Manager) | Position Monitoring
|  | Request to Update a Position | Manager Space
|  | Review Request (Compensation Analyst) | Compensation
|  | Review Request (HR Administrator) | Global Human Resources
Hire to Maintain
|  | Submit Hire Request | Manager Space
|  | Submit Rehire Request | Manager Space
|  | Reinstate | Employee Space
|  | Review Request (Manager) | Manager Space
|  | Review Request (Position Budget Manager) | Position Monitoring
|  | Review Request (HR Administrator) | Global Human Resources
|  | Complete Onboarding Tasks | Employee Space
|  | Complete Administrative Onboarding Tasks | Global Human Resources
|  | Validate Resource Transition Tasks | Global Human Resources
| Tracker I-9 |  | Tracker I-9
Transfer to Promote
|  | Request Promote | Manager Space
|  | Review Request (Parent Manager) | Manager Space
|  | Request Transfer | Manager Space
|  | Review Request (Position Budget Manager) | Position Monitoring
|  | Review Request (HR Administrator) | Global Human Resources
|  | Resource Completes Crossboarding | Employee Space
Benefit Event to Enrollment
|  | Initiate Open Enrollment Event | Benefits
|  | Complete Open Enrollment Benefit Elections | Benefits
|  | Submit Open Enrollment | Benefits
|  | Complete Life Event Enrollment Benefit Elections | Benefits
|  | Submit Qualifying Life Event Enrollment | Benefits
|  | Finalize Enrollment Event | Benefits
Employee Self Service to Maintenance
|  | Request Change | Employee Space
|  | Review Request (HR Administrator) | Global Human Resources
Qualifications to Skills
|  | Request Qualification Change | Qualifications
|  | Review Request (Manager) | Qualifications
Termination to Offboard
|  | Submit Resignation | Employee Space
|  | Review Request (Manager) | Manager Space
|  | Submit Termination Action | Manager Space
|  | Review Request (HR Administrator) | Global Human Resources
|  | Offboard Employee | Transition Management
Employee Inquiry to Resolution
Case Submission to Assignment
|  | Create Case in Employee Ask | Case Management
|  | Assign Case | Case Management
|  | Monitor Agent Queue | Case Management
|  | Create Case in Manager Ask | Case Management
Assignment to Case Resolution
|  | Review Case Notes and Attachments | Case Management
|  | Update or Add Case Notes | Case Management
|  | Resolve Case | Case Management
|  | Transfer Case to Agent | Case Management
|  | Escalate Case | Case Management
Compensation Planning to Payments
Compensation Structures Review to Assign
|  | Prepare Market Survey Request | Compensation
|  | Market Survey Process | Compensation
|  | Compensation Analysis | Compensation
|  | Salary Structure Review | Compensation
|  | Create New Salary Structure Iteration | Compensation
|  | Create New Salary Structure Version | Compensation
|  | Activate New Salary Structure Iteration | Compensation
|  | Copy Step and Grade Schedule | Compensation
|  | Mass Update Pay Steps | Compensation
|  | Update Work Assignment Pay Rates | Compensation
Step and Grade Schedules to Rate Progression
|  | Define Custom Groups for Step and Grade | Compensation
|  | Rate Progression Rules and Component Setup | Compensation
|  | Update Schedules with Rate Progression Rules | Compensation
|  | Model Pay Rate Changes | Compensation
|  | Review or Adjust Change Records | Compensation
|  | Update Work Assignments for Step and Grade | Compensation
Model Mass Pay Changes to Assignment
|  | Define Custom Groups for Mass Pay Changes | Compensation
|  | Model Mass Pay Rate Changes | Compensation
|  | Review and Adjust Mass Pay Change Records | Compensation
|  | Update Mass Pay Change to Work Assignments | Compensation
Standard Compensation Planning to Award
|  | Create Budget Records | Compensation
|  | Validate Resource Budgets | Compensation
|  | Mass Finalize And Make Available To Managers | Compensation
|  | Review Resource Budgets and Update Award | Compensation
|  | Internal Review with Upline Management | Compensation
|  | Submit Awards and Lump Sums | Compensation
|  | Upline Manager Review | Compensation
|  | Review and Adjust Budget | Compensation
|  | Review Pending Pay Rate Changes | Compensation
|  | Review Lump Sum Payouts | Compensation
|  | Finalize Lump Sum Payouts | Compensation
|  | Process Pay Rate Changes | Compensation
|  | Process Lump Sum Payouts to Payroll | Compensation
Incentive Compensation Planning to Award
|  | Enroll Resources into Incentive Program | Compensation Incentive Pay
|  | Review Pending Incentive Enrollments | Compensation Incentive Pay
|  | Finalize Incentive Enrollments | Compensation Incentive Pay
|  | Create Bonus Period | Compensation Incentive Pay
|  | Add, Approve, Maintain Bonus Objectives | Compensation Incentive Pay
|  | Complete and Approve Bonus Objectives | Compensation Incentive Pay
|  | Recalculate Incentive Enrollments | Compensation Incentive Pay
|  | Incentive Enrollment Updates | Compensation Incentive Pay
|  | Update External Incentive Metrics | Compensation Incentive Pay
|  | Calculate Incentive Payouts | Compensation Incentive Pay
|  | Maintain Incentive Payouts | Compensation Incentive Pay
|  | Finalize Incentive Payouts | Compensation Incentive Pay
|  | Request Special Incentive Payouts | Compensation Incentive Pay
|  | Submit Incentive Payments to Payroll | Compensation Incentive Pay
Calculate to Pay
|  | Assign Tax Deductions | Payroll
|  | Calculate Imputed Income | Payroll
|  | Import and Make Current all Time Records | Payroll
|  | Maintain Deductions | Payroll
|  | Calculate Overtime | Payroll
|  | Lock Payroll Schedule | Payroll
|  | Calculate Payments | Payroll
|  | Arrears Automation | Payroll
|  | Absence Plan Calculation | Payroll
|  | Print Payment and Remittance Advice | Payroll
|  | Transmit ACH and Positive Pay File | Payroll
|  | Close Absence Cycle | Payroll
|  | Close Payroll Cycle and Post to GL | Payroll
|  | Month-end GL Liability Update | Payroll
|  | Vendor Interface and Tax Payment | Payroll
Attendance to Time Entry
Request Leave to Complete Leave
|  | Request Leave of Absence | Absence Management
|  | Review Request (HR Administrator) | Absence Management
|  | Begin Leave | Absence Management
|  | Complete Leave | Absence Management
Work Safety to People Health
Safety Observations to Incidents
|  | Recognize Safe Behavior | Employee Safety
|  | Acknowledge and Validate Safe Behavior | Employee Safety
|  | Report Safety or Near Miss Observation | Employee Safety
|  | Evaluate Observation | Employee Safety
|  | Assign Investigator | Employee Safety
|  | Investigate and Update Observation | Employee Safety
|  | Complete Investigation | Employee Safety
|  | Generate Incident | Employee Safety
|  | Attach to existing Incident | Employee Safety
|  | Close the Observation | Employee Safety
Safety Incidents to Maintenance
|  | Create Incident | Employee Safety
|  | Update Incident | Employee Safety
|  | Request Input (Observation Only) | Employee Safety
|  | Enters Observation Input | Employee Safety
|  | Assign Investigator | Employee Safety
|  | Investigate and Update Incident (Employee) | Employee Safety
|  | Complete Investigation | Employee Safety
|  | Review or Complete Investigation and Update Incident | Employee Safety
|  | Create Follow-up Task | Employee Safety
|  | Mark Follow-up Task Complete | Employee Safety
|  | Mark Incident Complete | Employee Safety
|  | Flag for OSHA Reporting | Employee Safety
Health Components to Maintenance
|  | Assign Component or Series By Position | Occupational Health
|  | Assign Component or Series By Eligibility Group (Mass Assign) | Occupational Health
|  | Assign Component or Series By Location | Occupational Health
|  | Assign Component or Series By Employee Assignment | Occupational Health
|  | Update Health Component Results for Employee | Occupational Health
|  | Monitor and Update Overdue or Nearly Due Health Components | Occupational Health
|  | Review Health Component Notifications and Update | Occupational Health
|  | Review and Update Pending Health Components | Occupational Health
|  | Review and Update Refused Health Components | Occupational Health
Coaching to Grievence Resolution
Coaching Opportunity to Follow-up
|  | Enter Note on Employee Record | Employee Relations
|  | Create Coaching Event | Employee Relations
|  | Coaching Meeting | Employee Relations
|  | Marked Presented | Employee Relations
|  | Create New Corrective Action | Employee Relations
|  | Create Document (As Required) | Employee Relations
|  | Send for Review | Employee Relations
|  | Review Corrective Action (Direct Supervisor) | Employee Relations
|  | Review Corrective Action (HR Generalist) | Employee Relations
|  | Update Action or Document | Employee Relations
|  | Send for Review | Employee Relations
|  | Create Meeting | Employee Relations
|  | Corrective Action Meeting | Employee Relations
|  | Mark As Issued | Employee Relations
|  | Acknowledge | Employee Relations
|  | Enter Follow Up Date | Employee Relations
|  | Update Action with Additional Documentation | Employee Relations
Grievance to Resolution
|  | Create Grievance | Employee Relations
|  | Update Grievance or Step | Employee Relations
|  | Mark As Resolved | Employee Relations
Employee Development to Performance
Activities to Learning Plans
|  | Suggest an Activity | Learning and Development
|  | Review Request | Learning and Development
|  | Create or Maintain an Activity | Learning and Development
|  | Assign Evaluation | Learning and Development
|  | Create or Maintain Sessions | Learning and Development
|  | Create or Maintain Development Plan | Learning and Development
|  | Create or Maintain Certification | Learning and Development
|  | Create or Maintain a Checklist | Learning and Development
Enrollment to Learning Completion
|  | Make Training Available | Learning and Development
|  | Registration or Checklist Assignment | Learning and Development
|  | Enrollment to Activity | Learning and Development
|  | Review Request | Learning and Development
|  | Take Activity | Learning and Development
|  | Take Evaluation | Learning and Development
|  | Register for Specific Session | Learning and Development
|  | Review Request | Learning and Development
|  | Attend Session | Learning and Development
|  | Mark as Complete | Learning and Development
|  | Take Evaluation | Learning and Development
Development to Goals
|  | Create, Align, Cascade Organizational Goals | Goals Management
|  | Establish Employee Goals | Goals Management
|  | Assign and Align Organizational Goals | Goals Management
|  | Manage Employee Goals | Goals Management
|  | Establish or Edit Employee Goals | Goals Management
|  | Manage Resource Goals | Goals Management
Goals to Appraisal
|  | Manage Appraisal Policies | Performance Management
|  | Initiate Performance Appraisal | Performance Management
|  | Perform Appraisals | Performance Management
|  | Self-Evaluation | Performance Management
|  | Approval and Acknowledgement | Performance Management
|  | Monitor and Close Appraisal Process | Performance Management
Succession Planning | Succession Planning |  | Succession Planning
Workforce Management
Level 1 (Process Area) | Level 2 (Process - Flowchart) | Level 3 (Workflow Activities) | Module
Employee Data to Scheduling
Employee Refresh to Maintenance
|  | Update Employee Data | Time and Attendance
Shift Pattern to Assignment
|  | Define Shift Pattern or Assignment Form | Time and Attendance
|  | Update Shift Pattern Assignment | Time and Attendance
Shift Billboard
|  | Notify Supervisor of Shift Trade Intention | Time and Attendance
|  | Select Shift for Billboard Posting | Time and Attendance
|  | Identify and Post Selected Shifts to Billboard | Time and Attendance
|  | View and Claim Open Shifts | Time and Attendance
|  | Review Trade Details | Time and Attendance
Shift Trade
|  | Notify Supervisor of Intention to Trade | Time and Attendance
|  | Complete Electronic Shift Trade Form | Time and Attendance
|  | Review Trade Details | Time and Attendance
|  | Update Schedules | Time and Attendance
Attendance to Time Off Management
Time Off Management to Unplanned Absence
|  | Submit Time Off Request | Time and Attendance
|  | Cancel Time Off Request | Time and Attendance
|  | Approval Decision | Time and Attendance
|  | Notify Supervisor of Unplanned Absence | Time and Attendance
Attendance Management to HR Action
|  | Record Disciplinary | Time and Attendance
|  | HR Action | Time and Attendance
Time Collection to Payroll File Generation
Time Collection to Timesheet Entry
|  | Record Time | Time and Attendance
|  | Submit Timesheet | Time and Attendance
|  | Record Time and Work Details | Time and Attendance
|  | Entry on Timesheet | Time and Attendance
Attestation to Timesheet Approval
|  | Review Timesheet with Rejected Attestation | Time and Attendance
|  | Update Timesheet | Time and Attendance
|  | Review/Edit Reason for Exception | Time and Attendance
|  | Authorize Timesheet | Time and Attendance
Adjustments to Off Cycle Payroll
|  | Identify an Issue with Prior Pay | Time and Attendance
|  | Update Timesheet | Time and Attendance
|  | Request Off Cycle Pay | Time and Attendance
|  | Update Time Events | Time and Attendance
|  | Initiate Off Cycle Payroll Export | Time and Attendance
File Generation to Export
|  | Examine Timesheets | Time and Attendance
|  | Update and Approve Timesheets | Time and Attendance
|  | Initiate Payroll Export using Payroll Close Wizard | Time and Attendance
|  | Confirm Payroll File Generation and Transfer | Time and Attendance
WFM Application Configuration to Maintenance
Balance to Accruals Setup
|  | Balance Setup | Time and Attendance
|  | Accruals Setup | Time and Attendance
|  | Policy Setup | Time and Attendance
|  | Time Off Type Setup | Time and Attendance
|  | Blackout Team Calendar Setup | Time and Attendance
Employee to Skills Setup
|  | Employee Work Type Setup | Time and Attendance
|  | Employee Setup | Time and Attendance
|  | Employee Badge Setup | Time and Attendance
|  | Employee Data Definition Setup | Time and Attendance
|  | Employee Default Timesheet Setup | Time and Attendance
|  | Skill Types and Skills Setup | Time and Attendance
Labor Metric Security to Labor Setup
|  | Department Setup | Time and Attendance
|  | Project Setup | Time and Attendance
|  | Docket Setup | Time and Attendance
|  | Job Setup | Time and Attendance
|  | Labor Metric Security Setup | Time and Attendance
|  | Labor Shortcut Setup | Time and Attendance
Shift Creation to Shift Pattern Offset Setup
|  | Shifts Setup | Time and Attendance
|  | Shift Pattern Setup | Time and Attendance
|  | Shift Premium Zones Setup | Time and Attendance
|  | Shift Pattern Offset Setup | Time and Attendance
Payroll to Export Setup
|  | Hours Types Setup | Time and Attendance
|  | Time Codes Setup | Time and Attendance
|  | Cal Groups Setup | Time and Attendance
|  | Payroll Export Task Setup | Time and Attendance
|  | Pay Group Setup | Time and Attendance
|  | Override Types Setup | Time and Attendance
|  | Payroll Close Notifications Setup | Time and Attendance
|  | Payroll Close Tasks Setup | Time and Attendance
Holiday to Holiday Assignment Setup
|  | Holiday Setup | Time and Attendance
|  | Holiday Calendar Setup | Time and Attendance
|  | Holiday Calendar Employee Relationships Setup | Time and Attendance
|  | Holiday Roll Setup | Time and Attendance
|  | Holiday Assignment Setup | Time and Attendance
Clock to Reader Setup
|  | Reader Server Types to Reader Server Setup | Time and Attendance
|  | Reader Groups Setup | Time and Attendance
|  | Readers Setup | Time and Attendance
|  | Clock Validations Setup | Time and Attendance
|  | IP Address Groups Setup | Time and Attendance
|  | IP Address Whitelist Setup | Time and Attendance
Alerts to Distribution List Setup
|  | Alert Definitions Setup | Time and Attendance
|  | Distribution List Setup | Time and Attendance
Launch Pad Wizard to Launch Pad Activity Center Setup
|  | Launch Pad Wizard Setup | Time and Attendance
|  | Launch Pad Activity Center Setup | Time and Attendance
System Administration Setup to Maintenance
|  | Registry Maintenance Setup | Time and Attendance
|  | Field Localization Setup | Time and Attendance
|  | Date Format Setup | Time and Attendance
|  | Maintenance Forms Setup | Time and Attendance
|  | Popup Setup | Time and Attendance
|  | Job Scheduler Setup | Time and Attendance
|  | Quick Rule Editor Setup | Time and Attendance

## Implementation Summary
Offeror shall provide a concise high level summary of its proposed implementation approach.
Item | Vendor Response
Estimated Total Implementation Duration
Proposed Number of Phases to include the duration of those phases and whether some will run concurrent.
Proposed Implementation Start Assumption
Key Success Factors should include basis for success and who is responsible. Vendor or TRA.
Key Risks and Mitigation Approach
Major Assumptions
Trinity River Authority Resource Dependency Summary-TRA resouce dependency should include the KSA and duration or time commitment of the resources.
Narrative Response
Provide a concise summary of the proposed implementation approach and why it is appropriate for Trinity River Authority.
Insert vendor response here:

## Implementation Milestones
Proposed Implementation Milestones
Offeror shall describe the proposed implementation milestones and major deliverables.
Milestone | Description | Major Deliverables
1 | Discovery & Planning
2 | Design & Configuration – Finance/SCM
3 | Design & Configuration – HCM/Payroll/WFM, LMS
4 | Data Conversion Mock Cycles – Lawson V10
5 | Data Conversion Mock Cycles – UKG, Cornerstone
6 | Integration (ION Platform)
7 | Infor Velocity Suite
8 | Reporting (Birst) / Budgeting (Questica)
9 | Testing (SIT/UAT/Parallel Payroll, LMS)
10 | Organizational Change Mgmt. & Training
11 | Finance/SCM Go-Live
12 | HCM/Payroll, LMS Go-Live
13 | Post Go-Live Hypercare Complete (retainage release)

## Implementation Timeline
Proposed Implementation Timeline
Offeror shall provide a graphical view of the implementation timeline showing the major work efforts (i.e. Initiation, Configuration, UAT, SIT, etc.)

## Integration Implementation
Integration Implementation Approach
Offeror shall summarize how integrations will be planned, designed, built, and tested.
Area | Vendor Response
API / Interface Development Approach
Security / Authentication Approach
Integration Testing Approach
Integration Documentation Approach

## Project Governance
Project Governance Approach
Offeror shall describe the proposed project governance structure, meeting cadence, reporting, escalation, and control processes.
Governance Area | Vendor Response
Project Governance Structure
Executive Steering Committee Approach
Core Project Team Structure
Decision-Making Process
Project Team Meeting Cadence
Status Reporting Approach
Risk and Issue Management Approach
Action Item Tracking Approach
Change Control Process
Escalation Process
Quality Assurance Approach
Communication Management Approach
Vendor / Subcontractor Governance Approach

## Data Migration Approach
Data Migration Implementation Approach
Offeror shall summarize how legacy data migration will be planned, executed, validated, reconciled, and supported. Legacy systems include: Maximo, UKG, Procureware, Cornerstone, (Perceptive Content upgrade to Laserfiche in progess).
Area | Vendor Response
Data Migration Methodology
Legacy Data Assessment Approach
Data Quality Assessment Approach
Data Cleansing Assumptions
Source-to-Target Mapping Approach
Mock Migration / Trial Load Approach
Data Validation and Reconciliation Approach
Cutover Migration Approach
Key Assumptions / Dependencies

## Testing & UAT
Testing and UAT Approach
Offeror shall describe its proposed approach to include phases for planning, executing, documenting, and supporting testing and UAT.
Testing Area | Vendor Response
Overall Testing Methodology
Test Plan Approach
Test Script Development Approach
Unit Testing Approach
System Testing Approach
Integration Testing Approach
UAT Support Approach
Test Execution Reporting Approach

## Training & OCM
Training and Organizational Change Management Approach
Offeror shall describe how it will train Trinity River Authority users, administrators, and support staff, and how it will support organizational readiness and adoption.
Area | Vendor Response
Training Strategy
End-User Training Approach
Training Material Development Approach
Training Delivery Method | Onsite / Remote / Hybrid
Knowledge Transfer Approach to include
Organizational Readiness Assessment Approach
OCM Strategy
Stakeholder Impact Assessment
Communication Plan Approach

## Go-Live & Support
Go-Live, Cutover, and Post-Go-Live Support Approach
Offeror shall describe its proposed go-live, deployment, cutover, stabilization, and post-go-live support approach.
Area | Vendor Response
Go-Live Strategy
Cutover Planning Approach
Production Readiness Criteria
Final Data Load Approach
Go / No-Go Decision Process
Post-Go-Live Issue Management

## TRA Resources Needed
Trinity River Authority Resource Needs
Offeror shall identify the expected Trinity River Authority resources needed to support the implementation.
Role / Resource Type | Estimated Time Commitment | Responsibilities / Activities
Executive Sponsor
Project Manager
Business SMEs
IT Technical Lead
Integration / API Resources
Data / Reporting Resources
Testing / UAT Participants
Training Participants
Change Management / Communications Resources
Other

## Milestone Pricing
Implementation services must be priced and paid on a milestone/deliverable-acceptance basis; the Authority will not pay a flat monthly, quarterly, or annual fee for implementation services.
Milestone / Deliverable | Target Completion Date | Fixed Price | % of Total Contract Value
Discovery & Planning Complete
Design & Configuration Complete – Finance/SCM
Design & Configuration Complete – HCM/Payroll/WFM, LMS
Data Conversion Mock Cycles Complete – Lawson V10
Data Conversion Mock Cycles Complete – UKG, Cornerstone, Maximo
Complete Integration (ION Platform)
Infor Velocity Suite Deployed
Reporting (Birst) / Budgeting (Questica) Complete
Testing Complete (SIT/UAT/Parallel Payroll, LMS)
Organizational Change Mgmt. & Training Complete
Finance/SCM Go-Live
HCM/Payroll, LMS Go-Live
Post Go-Live Hypercare Complete (retainage release)
TOTAL Implementation Services (100%) |  | 0

## References
References
Section 8.2
Respondents shall provide a minimum of three (3) client references from public sector entities (municipality, county, special district, water/river authority, or comparable government body) for which the bidder delivered **concurrent or closely sequenced FSM and Payroll implementations** References limited to single-module engagements (e.g., FSM-only or HCM-only) will be considered supplemental, not primary, evidence of qualification. For each reference, specify project duration, go-live date, and whether all three workstreams were delivered by your firm directly or through subcontracted partners. For each reference the proposer shall provide:
Reference 1
Client Name:
Contact Name/Title:
Phone / Email:
Modules Implemented:
Prior System(s) Replaced:
Project Dates (Start/Go-Live):
Workstream /Module Engagement
Reference 2
Client Name:
Contact Name/Title:
Phone / Email:
Modules Implemented:
Prior System(s) Replaced:
Project Dates (Start/Go-Live):
Workstream /Module Engagement
Reference 3
Client Name:
Contact Name/Title:
Phone / Email:
Modules Implemented:
Prior System(s) Replaced:
Project Dates (Start/Go-Live):
Workstream /Module Engagement